7 September 2012

[20-12]

Administrative Assessment Report – Proposal P1022

Primary Production & Processing Requirements for Approved Raw Milk Products

| Brief Description of Proposal: To consider permissions for the production and sale of approved raw milk products. The current state and territory exemption allowing the production and sale of raw milk will be reviewed. | Potentially affected Standards: 1.2.3 – Mandatory Warning and Advisory Statements and Declarations 1.2.4 – Labelling of Ingredients 1.6.1 – Microbiological Limits for Food 4.2.4 – Primary Production and Processing Standard for Dairy Products 4.2.4A – Primary Production and Processing Requirements for Specific Cheeses |
| --- | --- |
| Procedure: Major The proposal involves such scientific or technical complexity that it is necessary to adopt this procedure. | Estimated total hours: 3650 Reasons why: Requires extensive consultation with stakeholders and the engagement of a technical working group. | Estimated start work: March 2012 |

Other Comments or Relevant Matters: P1007 amended Standards 4.2.4 and 4.2.4A to allow for the production of category 1 cheeses only i.e. cheeses for which the properties and/or processing factors eliminate pathogens that may have been present in the raw milk. This proposal considers other raw milk products.

Decision

Proposal prepared Date: 30 August 2012

Consultation & assessment timeframe

Proposed length of public consultation periods 1st call for submissions (8 weeks) 2nd call for submissions (8 weeks) The Raw Milk Products SDC will provide advice throughout this work

Proposed timeframe for assessment: Commence assessment (clock start) Early September 2012 Completion of assessment Late July 2013 Public comment Early August 2013 – Early October 2013 Preparation of draft food reg measure Early March 2014 Public comment Mid-March 2014 – Mid-May 2014 Board to complete approval Late October 2014 Notification to Forum Early November 2014 Anticipated gazettal if no review requested Mid-January 2015